## general_report
SEF Jira
Displaying 55 issues at 23/Aug/15 11:59 AM.
Project | Key | Summary | Priority | Resolution | Assignee | Reporter | Creator | Created | Last Viewed | Updated | Description | Story Points | Sprint
IFB299 021 | TWOONE-67 | Mobile Layout | Must Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-19 15:26 | 2015-08-23 11:59 | 2015-08-22 15:33 | As a user, I want to be able to view the page on a mobile device so that I can interact with it on the go | 8 | Iteration 1
IFB299 021 | TWOONE-53 | Sign Up (Profile Picture) - Owner | Could Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-12 14:23 |  | 2015-08-21 09:16 | As a property owner, I want to upload a profile picture so that I can personalise my profile | 4
IFB299 021 | TWOONE-52 | Sign Up (Profile Picture) - Tenant | Could Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-12 14:21 |  | 2015-08-21 09:16 | As a prospective tenant, I want to upload a profile picture so that I can personalise my profile | 4
IFB299 021 | TWOONE-51 | Sign Up Property Owner | Should Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-12 14:04 |  | 2015-08-22 16:11 | As a property owner, I want to sign up to the site so that I can lease out my property's | 5 | Iteration 3
IFB299 021 | TWOONE-50 | Sign Up Tenant | Must Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-12 14:01 | 2015-08-12 14:03 | 2015-08-22 15:32 | As a prospective tenant, I want to sign up to the site, so that I can save potential properties | 8 | Iteration 1
IFB299 021 | TWOONE-49 | Upload property picture | Should Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-12 13:59 | 2015-08-12 14:02 | 2015-08-22 15:39 | As a staff member, I want to be able to upload a picture of a property so that it appears more desirable. | 4 | Iteration 2
IFB299 021 | TWOONE-47 | Send Email from Tenant to Owner | Must Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:57 | 2015-08-12 13:56 | 2015-08-22 15:30 | As a prospective tenant, I want to send an email or text message to the property owner so that I can organise a house inspection | 6 | Iteration 1
IFB299 021 | TWOONE-46 | Property on Interactive Map | Could Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:57 |  | 2015-08-21 09:16 | As a prospective tenant, I want to view the potential property on an interactive map so that I can visualise the properties's location | 8
IFB299 021 | TWOONE-45 | Landlord Contact Details | Could Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:56 | 2015-08-12 13:55 | 2015-08-21 09:15 | As a prospective tenant, I want to view the contact details of the landlord so that I can organise a house inspection | 1
IFB299 021 | TWOONE-44 | View Floorplan | Should Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:56 |  | 2015-08-22 15:39 | As a prospective tenant, I want to view the floorplan of the property so that I can visualise the layout and make an informed decision | 4 | Iteration 2
IFB299 021 | TWOONE-43 | List of Images | Trivial | Fixed | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:55 |  | 2015-08-19 14:39 | as prospective tenant, I want to view a list of images representing the property so that I can make an informed decision of commitment
IFB299 021 | TWOONE-42 | Send Ad-hoc Notifications | Should Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:55 |  | 2015-08-22 16:11 | As a property owner, I want to notify tenants via email or text of open house events so that I can lease off the property | 9 | Iteration 3
IFB299 021 | TWOONE-41 | Send Automatic Notifications | Should Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:54 |  | 2015-08-22 16:19 | As prospective tenant, I want to receive notifications of when saved properties host open house events so that I can inspect the potential property | 6 | Iteration 3
IFB299 021 | TWOONE-40 | Save Property | Trivial | Fixed | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 10:54 |  | 2015-08-19 14:38 | As a prospective tenant, I want the ability to save a favourite property so that I can view the property more easily
IFB299 021 | TWOONE-39 | Add Property | Must Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:43 |  | 2015-08-22 15:24 | as a property manager i wish to be able to add a property for approval so that i can rent it/ sell it | 8 | Iteration 1
IFB299 021 | TWOONE-38 | Update Price | Must Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:41 | 2015-08-22 16:04 | 2015-08-22 16:04 | as a manager/owner i wish to be able to update the price on a property so that i can make my property more desirable | 4 | Iteration 1
IFB299 021 | TWOONE-37 | View Price | Must Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:40 |  | 2015-08-22 15:16 | as a user i wish to be able to see the price of a property so that i can decide whether to buy or rent | 2 | Iteration 1
IFB299 021 | TWOONE-36 | written feedback creation | Trivial | Fixed | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:38 |  | 2015-08-19 14:36 | as a tenant in a property i wish to be able to provide feedback so that i can give perspective to potential tenants
IFB299 021 | TWOONE-35 | Read Written Feedback | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:37 |  | 2015-08-22 15:46 | as a user i wish to be able to read written feedback on a property so that i can see a tenants perspective of a property | 3 | Iteration 2
IFB299 021 | TWOONE-34 | Manage Property Availability Ad-hoc | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:36 | 2015-08-22 16:24 | 2015-08-22 16:24 | as a manager i wish to be able to set a property available date so that i can advertise it to have tenants in ASAP | 4 | Iteration 3
IFB299 021 | TWOONE-33 | View Date Available | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:35 |  | 2015-08-22 15:58 | as a user i wish to be able to know the date at which a property becomes available so that i can plan whether to move into it | 4 | Iteration 2
IFB299 021 | TWOONE-32 | View Inspection Dates | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:32 |  | 2015-08-21 08:44 | as a user i wish to be able to view inspection dates and times so that i can attend those events | 3 | Iteration 2
IFB299 021 | TWOONE-31 | breadcrumb | Could Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:31 |  | 2015-08-21 09:15 | as a user i want to be able to view a breadcrumb trail so that i can easily navigate back to previous pages i have viewed | 5
IFB299 021 | TWOONE-30 | street view | Could Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:20 |  | 2015-08-21 09:14 | as a prospective user i wish to be able to view a street view of the property so that i have a better sense of direction to the property | 5
IFB299 021 | TWOONE-29 | View Parking Space Numbers | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:14 |  | 2015-08-22 15:54 | as a user i wish to be able to see how many parking spaces are available in a property to know whether it meets my requirements | 2 | Iteration 2
IFB299 021 | TWOONE-28 | View Bathroom Numbers | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:13 |  | 2015-08-22 15:54 | as a user i wish to know how many bathrooms a property has so that i can see if the property meets my needs | 2 | Iteration 2
IFB299 021 | TWOONE-27 | property bedroom | Trivial | Fixed | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:12 |  | 2015-08-19 14:30 | as a user i wish to be able to view the number of bedrooms in a property so that i know if the property is big enough
IFB299 021 | TWOONE-26 | List Most Popular Properties | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:11 |  | 2015-08-22 16:10 | as a user i wish to be able to see the most popular properties so that i can see what is desirable | 7 | Iteration 3
IFB299 021 | TWOONE-25 | List Personally Recently Viewed | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:08 |  | 2015-08-22 16:10 | as a user i wish to be able to see recently viewed properties so that i can navigate back to them with ease | 7 | Iteration 3
IFB299 021 | TWOONE-24 | Save Property | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 10:08 |  | 2015-08-22 15:50 | as a prospective tenant i wish to be able to save properties to a list so that i can review them | 4 | Iteration 2
IFB299 021 | TWOONE-23 | View Saved Properties | Should Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 09:54 |  | 2015-08-21 08:42 | As a prospective tenant, I want to view my saved properties so that I can inspect them in the near future | 4 | Iteration 2
IFB299 021 | TWOONE-22 | share to social media | Could Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-10 09:50 | 2015-08-10 09:52 | 2015-08-21 09:13 | As a house owner I want to be able to share a house to social media so that I can increase it's exposure. | 8
IFB299 021 | TWOONE-21 | sort by inspection date | Could Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-10 09:48 | 2015-08-10 09:48 | 2015-08-21 09:11 | As a prospective tenant I want to be able to view accommodation item results in order of inspection dates so that I can easily plan my inspections | 5
IFB299 021 | TWOONE-20 | View Property Details | Must Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 09:47 |  | 2015-08-22 16:44 | As a user i wish to be able to see the general details of a property in order to evaluate its value | 2 | Iteration 1
IFB299 021 | TWOONE-19 | Location based on Radius Distance | Could Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 09:45 |  | 2015-08-21 09:10 | As prospective tenant, I want to search for a property based on desired radius from location so that I can find the desired property | 8
IFB299 021 | TWOONE-18 | View Property Manager Contact | Must Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 09:44 |  | 2015-08-22 15:17 | as a prospective tenant i wish to be able to see the contact details of the property manager so that i can get in touch with them | 2 | Iteration 1
IFB299 021 | TWOONE-17 | tenant should be able to book an inspection for the house | Could Have | Unresolved | Unassigned | Sagar Bhindi | Sagar Bhindi | 2015-08-10 09:44 |  | 2015-08-21 09:09 | As a prospective tenant I want to be able to view all the dates available for inspection of a house so that I can inspect the property | 6
IFB299 021 | TWOONE-16 | View Bedroom Numbers | Should Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-10 09:42 | 2015-08-10 09:42 | 2015-08-22 15:53 | As a prospective tenant I want to be able to view how many bedrooms a leased whole house has so that I can determine if it's big enough for me. | 2 | Iteration 2
IFB299 021 | TWOONE-15 | Filter Properties by Price | Must Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-10 09:41 | 2015-08-10 09:41 | 2015-08-22 15:26 | As a prospective tenant I want to be able to filter accommodation item results by price so that I can focus on the properties I can afford | 6 | Iteration 1
IFB299 021 | TWOONE-14 | Advertisement | Could Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 09:36 |  | 2015-08-21 09:08 | As a property manager, I want to display advertisement so that I can increase revenue for the website | 8
IFB299 021 | TWOONE-13 | System Admin Revoke Rights | Could Have | Unresolved | Unassigned | Sagar Bhindi | Sagar Bhindi | 2015-08-10 09:34 |  | 2015-08-22 16:13 | As a system administrator I want to be able to revoke rights from current staff members so that I can maintain organisational security | 5 | Iteration 3
IFB299 021 | TWOONE-12 | View Nearby Facilities | Could Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 09:33 |  | 2015-08-22 16:13 | As a prospective tenant i want to be able to view local facilities in the area so that i know what is nearby | 9 | Iteration 3
IFB299 021 | TWOONE-11 | Filter Property Type | Should Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-10 09:33 | 2015-08-10 09:33 | 2015-08-22 15:44 | As a prospective tenant I want to be able to filter property results by type so that I can more easily find the property which suits me. | 7 | Iteration 2
IFB299 021 | TWOONE-10 | View Location Details | Must Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 09:32 |  | 2015-08-22 15:15 | As a prospective tenant i want to be able to view the location data of the property so that i can know where it is situated geographically | 3 | Iteration 1
IFB299 021 | TWOONE-9 | System Admin Assigning Rights | Could Have | Unresolved | Unassigned | Sagar Bhindi | Sagar Bhindi | 2015-08-10 09:32 |  | 2015-08-22 16:12 | As the system administrator (David) I want to be able to provide the staff members with the rights to make changes to the properties to ensure efficient and easier property management | 5 | Iteration 3
IFB299 021 | TWOONE-8 | Edit Tenant Account Profile | Must Have | Unresolved | Unassigned | Lucas Nielsen | Lucas Nielsen | 2015-08-10 09:31 | 2015-08-21 08:21 | 2015-08-22 15:33 | As a prospective tenant, I want to edit my profile so that I my personal information is up to date | 6 | Iteration 1
IFB299 021 | TWOONE-7 | View Property Results as Map | Should Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-10 09:30 | 2015-08-10 09:30 | 2015-08-22 15:49 | As a prospective tenant I want to be able to view property search results as a map so that I can evaluate them based on locality | 8 | Iteration 2
IFB299 021 | TWOONE-6 | Write Tenant Feedback | Should Have | Unresolved | Unassigned | Sagar Bhindi | Sagar Bhindi | 2015-08-10 09:26 |  | 2015-08-22 15:47 | As a current tenant I want to be able to provide a feedback on the property I leased so that i can express my opnions. | 4 | Iteration 2
IFB299 021 | TWOONE-5 | View Property Rating | Must Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 09:25 | 2015-08-12 16:29 | 2015-08-22 15:15 | As a prospective tenant i want to be able to view a rating of a property so that i can make a more informed decision about the overall nature of the property | 2 | Iteration 1
IFB299 021 | TWOONE-4 | Picture Gallery | Should Have | Unresolved | Unassigned | Thomas Parker | Thomas Parker | 2015-08-10 09:23 | 2015-08-10 09:50 | 2015-08-22 15:37 | As a prospective tenant i want to be able to view all pictures of a property in a slideshow so that i can see a property on one page | 5 | Iteration 2
IFB299 021 | TWOONE-3 | Signing Lease Document | Could Have | Unresolved | Unassigned | Sagar Bhindi | Sagar Bhindi | 2015-08-10 09:23 |  | 2015-08-22 16:13 | As a property owner I want to be able to sign the lease document so that I have a proof of contract with the tenant | 4 | Iteration 3
IFB299 021 | TWOONE-2 | Filter Bedrooms | Should Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-10 09:14 | 2015-08-21 08:37 | 2015-08-22 15:44 | As a prospective tenant I want to be able to filter by a bedroom number range so that I can find a property that suits me. | 6 | Iteration 2
IFB299 021 | TWOONE-1 | View Property Photos | Must Have | Unresolved | Unassigned | Ehren Hyde | Ehren Hyde | 2015-08-05 16:37 | 2015-08-10 09:25 | 2015-08-19 15:08 | As a prospective tenant I want to view a property's photographs in order to evaluate it | 3 | Iteration 1
Generated at Sun Aug 23 11:59:44 EST 2015 by Ehren Hyde using JIRA 6.2.7#6265-sha1:91604a8de81892a3e362e0afee505432f29579b0.